## Slide 1: LDA JMI Project

## Slide 2: Overview
Will be looking at demographic information for profiling
Will be doing analysis on MIC values based on profiles
Will be using NN to predict resistance categories based on/not on profiles

## Slide 3: Preprocessing
Convert all Gene values from pos->1 and neg->0
Find and label isolate as containing ESBL (0), containing carbapenemase (1), both (2), or neither (3)
Convert all isolate resistance categories into a 0 (NA), 1 (R), 2 (I), or 3 (S)
Find and record all MIC values for the isolates, including missing values. (may happen during analysis or before)
Sort the demographic data into groups, and give each group an id.
Either add all preprocessed data to SQL database, or to multiple csv files.

## Slide 4: Timeline
1. 1 - 2 weeks
2 and 3. 1 - 2 weeks
4. 1 week
5. 2 weeks
Total is 5 - 7 weeks

## Slide 5: Groups for split (2 and 3)
Analysis
  Karan Pahlani
  Evan Walser-Kuntz
  Cory Kromer-Edwards
NN
  Jace Neubaum
  Andrew West
  Cory Kromer-Edwards

## Slide 6: NN in 3
Input:
All 1, -1 genes
Whether isolate has ESBL, Carba., neither, or both
Output:
0 -> NA
1 -> Resistant
2 -> Intermediate
3 -> Susceptible

## Slide 7: NN in 4
Input:
All 1, -1 genes
Whether isolate has ESBL, Carba., neither, or both
MIC values
Demographic ID
Output:
0 -> NA
1 -> Resistant
2 -> Intermediate
3 -> Susceptible

## Slide 8: What to include in paper
Analysis results from demographic info and MIC values
NN results from 3 as a preliminary
NN results from 4 to see if adding information helped